## Summary
Servex - Technical / Security / Architecture Audit
Scope: SQL package and documentation only. Servex frontend, auth code and tests were NOT INSPECTED. Nothing was executed against any database. Not a score or ranking.
Severity | Total | Confirmed | Conditional
P0 | 0 | 0 | 0
P1 | 1 | 0 | 1
P2 | 3 | 3 | 0
P3 | 11 | 10 | 1
INFO | 4 | 3 | 1
Total | 19 | 16 | 3
Verification checklist
Open | 18
In progress | 0
Done | 0
Blocked | 0
Total checks | 18
Tabs: Findings ¦ State Machine ¦ RLS Audit ¦ Privacy ¦ Marketplace Risks ¦ Testing ¦ Verification Checklist ¦ Technical Fix Order
Evidence line numbers refer to the SQL package in the audit workspace (backend/migrations), which may differ from the repo's claude22 SQL (verify).
Edit the Status column on the Verification Checklist tab; counts above update automatically.

## Findings
ID | Severity | Type | Component | Evidence (file:line, my SQL copy) | Why it matters | Confidence | Verify in real repo?
S-01 | P2 | Confirmed | RLS / privacy | profiles_select 0005:81-82 allows provider_visible(id); table-wide SELECT grant | Any signed-in user can read the full profile row (email; phone once populated) of any approved provider | High | YES
S-02 | P2 | Confirmed | RLS / privacy | pp_select 0005:96; base_lat/base_lng 0002:80 | All signed-in users can read provider base coordinates (home/base location exposed) | High | YES
S-03 | P2 | Confirmed | Identity link (KI-016) | 0005:84 forces phone is null on client insert; no code reads auth.users except the FK at 0002:14 | Verified phone is never copied into profiles.phone; only link to verified identity is the id FK | High | YES
S-04 | P3 | Confirmed | Duplicate requests | Guard only in RPC (0004:97); unique indexes 0003:201,276,277,385 cover quotes/payments/disputes, not open jobs | Concurrent create_job calls could both pass the duplicate check and the open-request cap | Medium (by reading) | YES
S-05 | P3 | Confirmed | Locking | approve/send/reject_quote lock quote then job (0004:201->203, 225->227, 252->254); create_quote locks job first (0004:167) | Inconsistent lock order; deadlock possible under concurrency | Medium | YES
S-06 | P3 | Confirmed | Input bounds | cancellation_reason 0003:22; history note 0003:41; p_note/p_reason (0004:110,127,248,370) uncapped | Authenticated users can store arbitrarily large text | High | YES
S-07 | P3 | Confirmed | Inspection photos | ip_insert 0005:142 checks inspection ownership only; storage_path unconstrained | Metadata can point to any path string; reads still gated by (unexecuted) Storage RLS | Medium | YES
S-08 | P3 | Confirmed | Reports | disputes_insert_report 0005:170 | Any user can file unlimited reports against any user; no dedupe or rate limit | High | YES
S-09 | P3 | Confirmed | Payments visibility | payments_select 0005:156, table-wide SELECT | Customers see platform_commission and provider_earnings; sensitive given undecided revenue model | Medium | YES
S-10 | P3 | Confirmed | Account deletion | profiles.id ON DELETE CASCADE from auth.users (0002:14) vs 14 ON DELETE RESTRICT FKs (0003) | Deleting an auth user with history fails; no erasure/anonymisation strategy beyond an admin status flag | Medium | YES
S-11 | P3 | Confirmed | Prototype row | ('AWAITING_PAYMENT','PAID','customer') 0003:68 | Customer-actor payment transition exists for demo only; remove when payment_mode = gateway | High | YES
S-12 | P3 | Confirmed | Seed | tools/generate_seed.py and seed.sql use crypt('DemoPass#2026',...), guarded only by a comment | Running the seed anywhere real creates known-password accounts | High | YES
S-13 | P3 | Confirmed | Test defect (unexecuted) | tests/sql/001_behavior.test.sql first throws_ok expects 23503 | CHECK constraints evaluate before FK checks so 23514 expected; possible pgTAP privilege issues under SET ROLE | Medium | NO (own file)
S-14 | INFO | Confirmed | SQL injection | grep: no EXECUTE of user input; only format('%I') over fixed arrays in migrations | No injection path found in available SQL | High | YES
S-15 | INFO | Confirmed | Grants / RLS | grep: no 'to anon' / 'to public'; static checker: RLS enabled on 26/26 tables; definer functions pin search_path | Structural only (never executed) | High | YES
S-16 | INFO | Confirmed | Admin | profiles_insert allows customer/provider only; update grant excludes role/status; no function sets role='admin' | No client path to admin found; admin bootstrap is NOT IMPLEMENTED | High | YES
C-01 | P1 | Conditional | Market hardcoding | Phone regex +9627 (0002:16); cities amman/irbid (0001:7); currency='JOD' (0003:260,303); Asia/Amman (0004:32,33,317); name_ar NOT NULL (0002:51,62); preferred_language ar/en default ar (0002:20) | If used for Israel-first English-first: every payment insert fails, catalogue needs Arabic names, +972 phones/cities rejected, 'he' not allowed. Current-repo relevance UNKNOWN | High (code) / UNKNOWN (relevance) | YES
C-02 | P3 | Conditional | Israel considerations | No tax/VAT fields, no Israel-specific locale/weekend handling (legal requirements RESEARCH_REQUIRED) | Possible gaps for the Israel market; nothing asserted about law | Low | YES
C-03 | INFO | Conditional | Stale documentation | Older docs say Jordan/Arabic-first | Must not be treated as proof of current implementation | n/a | YES

## State Machine
Current State | Action | Actor | Next State | Evidence | Risk
REQUESTED | Accept (transition_job) | provider | ACCEPTED | 0003:54+ | Requires approved provider (trigger)
REQUESTED | Decline | provider | DECLINED | matrix | None
REQUESTED | Cancel (cancel_job) | customer | CANCELLED | matrix | None
REQUESTED | Expire (expire_stale_jobs) | system | EXPIRED | matrix | Cron not implemented
ACCEPTED | En route | provider | EN_ROUTE | matrix | None
ACCEPTED / EN_ROUTE / ARRIVED / INSPECTION | Cancel | customer or provider | CANCELLED | matrix | No cancellation fees (NOT IMPLEMENTED)
EN_ROUTE | Arrive | provider | ARRIVED | matrix | No location proof
ARRIVED | Start inspection | provider | INSPECTION | matrix | None
INSPECTION | Send quote (send_quote) | provider | QUOTE_SENT | matrix + trigger prerequisites | None
QUOTE_SENT | Approve (approve_quote) | customer | AWAITING_PAYMENT | matrix | Idempotent
QUOTE_SENT | Cancel | customer or provider | CANCELLED | matrix | None
QUOTE_SENT | Expire | system | EXPIRED | matrix | Cron not implemented
QUOTE_SENT | Reject (reject_quote) | customer | stays QUOTE_SENT | reject_quote | Provider may re-quote
AWAITING_PAYMENT | Pay (pay_demo) | customer (prototype) or system (gateway) | PAID | 0003:68-69 | S-11; no payment expiry (NOT IMPLEMENTED)
AWAITING_PAYMENT | Cancel | customer | CANCELLED | matrix | None
PAID | Start work | provider | IN_PROGRESS | matrix | None
PAID | Dispute | customer | DISPUTED | matrix | Cancel intentionally not allowed after payment
IN_PROGRESS | Complete (complete_job) | provider | COMPLETED | matrix + payment check | Provider can complete without customer confirmation
IN_PROGRESS / COMPLETED | Dispute (open_dispute) | customer or provider | DISPUTED | matrix | Time window applies to COMPLETED
DISPUTED | Resolve (resolve_dispute) | admin | COMPLETED or CANCELLED (+refund status) | 0004:391, :416 | Refund is a status flag only; partial refunds NOT IMPLEMENTED
DECLINED / CANCELLED / EXPIRED | (none) | none | none | static checker: no outgoing edges | Terminal

## RLS Audit
Table | SELECT | INSERT | UPDATE | DELETE
profiles | Self; admin; job counterpart; approved providers (S-01) | Self, role limited, phone NULL | Own cols (name, avatar, email, language) | None
customer_profiles | Self / admin | Self (customer) | Self | None
provider_profiles | Approved / self / admin (S-02) | Self, pending, zeroed | Own non-protected cols | None
provider_* child tables | Visible provider / self / admin | Self | Self | Self
categories, services | Active; admin all | Admin | Admin | None
jobs | Parties / admin | None (RPC) | None (RPC) | None
quotes, quote_items | Provider own; customer non-draft | None (RPC) | None (RPC) | None
payments, invoices, payment_events | Parties / admin; events admin only | None | None | None
reviews | Author / subject / admin; public if approved provider | None (RPC) | None | None
disputes | Parties / opener / admin | Reports only (S-08) | None | None
notifications | Recipient | None | read_at only | None
audit_logs, app_settings | Admin / invisible | None | None | None

## Privacy
Data | Who can access / what | Why it matters | Verify in real repo?
Phone | Counterparties and anyone viewing an approved provider; currently NULL (S-03) | Contact details before a job | YES
Email | Same exposure as phone (S-01) | Unverified, client-editable | YES
Provider coordinates | All authenticated users (S-02) | Provider home/base location | YES
Customer exact job location | Two job parties and admin | Expected | no
Customer default address | Self and admin only | OK | no
Payment data | No card data exists; payment rows visible to parties; commission columns visible (S-09) | Revenue model undecided | YES
Identity documents | NOT IMPLEMENTED | Verification evidence has no storage model | n/a
Inspection photos | Parties and admin (Storage policy, unexecuted) | Private bucket | YES
Portfolio images | Bucket is public (0006:6) | By design | YES
Quotes, reviews, history | Per RLS | OK | YES

## Marketplace Risks
Group | Area | Status
Provider | Profile | Implemented (SQL draft)
Provider | Categories / specialties | Implemented (SQL draft)
Provider | Service area | Partial: radius filter; neighbourhoods stored but not used for filtering
Provider | Availability | Partial: weekly windows only, no exceptions
Provider | Verification | Partial: status + admin RPC; no evidence documents
Provider | Ratings | Implemented (SQL draft)
Provider | Portfolio | Partial: table + bucket
Customer | Request / provider selection | Implemented (SQL draft)
Customer | Location | Partial: raw lat/lng, not validated against city
Customer | Quote / completion / review | Implemented (SQL draft)
Customer | Payment | Simulated
Platform | Admin | Partial: RPCs exist; no bootstrap; UI unknown
Platform | Disputes | Partial
Platform | Cancellation | Partial: no fees
Platform | Refunds | Partial: status only
Platform | Commission | Partial: configurable, default 0, no payout
Platform | Fraud prevention / fake providers | Partial: approval gate and open-request cap only
Platform | Fake reviews | Partial: completed-job gating; demo payments make collusion free
Platform | Duplicate requests | Partial (S-04)
Frontend aspects | All | Unknown / not inspectable

## Testing
Category | Exists | Executed | Passed | Real Supabase
Static structural checker (static_check.py) | EXISTS | YES | YES (structure only) | n/a
Seed generator assertions | EXISTS | YES | YES | n/a
pgTAP DB/RLS tests (001_behavior.test.sql) | EXISTS (18 assertions) | NO | n/a | NO; S-13 defect likely
Claimed PostgreSQL 16 behavioural tests | UNKNOWN | UNKNOWN | UNKNOWN | NO (substitute is not Supabase)
Auth / unit / integration / E2E / browser / responsive | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN
Role-boundary / RLS tests | Partial (few pgTAP assertions) | NO | n/a | NO

## Verification Checklist
# | Check | Status | Notes
1 | Obtain full ZIP; inspect package.json, src/, routes, hooks, services | Open
2 | Diff repo claude22 SQL against my copy; record differences | Open
3 | Re-test S-01 to S-12 against the repo's SQL | Open
4 | Confirm market: Israel / English-first; check +972 phone validation, cities, currency, timezone, name_ar, languages | Open
5 | Verify English/LTR implementation, accessibility, responsive layout | Open
6 | Inspect auth: login, OTP, registration, role selection, logout, session storage | Open
7 | Confirm KI-016 in repo and how verified phone is stored | Open
8 | Inspect Customer, Provider and Admin pages; route guards; role manipulation from client | Open
9 | Verify admin bootstrap path; no client can self-assign admin | Open
10 | Inspect Supabase client and env files; ensure no service-role key in client bundle | Open
11 | Inspect demo-flag isolation (demo OTP, mock data, simulated payment) | Open
12 | Inspect upload handling and dangerouslySetInnerHTML / XSS surfaces | Open
13 | Run TypeScript, ESLint, unit tests, E2E; record outputs | Open
14 | Apply migrations to LOCAL Supabase (not production) and run pgTAP/RLS tests | Open
15 | Verify Storage policies and Realtime behaviour | Open
16 | Compare frontend job statuses/types with SQL enums and transitions | Open
17 | Run dependency audit; find unused dependencies | Open
18 | Verify documentation vs code (SESSION_HANDOFF.md, FILE_MAP.md) | Open

## Technical Fix Order
Order | Verify / fix | Findings
1 | Get the real repo and diff the SQL (everything is conditional until then) | All
2 | Confirm market and language, then decide C-01 | C-01
3 | Execute migrations and tests on local Supabase (gate for all SQL findings) | S-13, all SQL
4 | Phone linking with privacy exposures | S-03, S-01, S-02
5 | Race and lock order; input bounds, reports, commission visibility | S-04, S-05, S-06, S-07, S-08, S-09
6 | Deletion strategy, prototype row, seed guard (before any non-dev deployment) | S-10, S-11, S-12
7 | Fix the test defect when tests are first run | S-13